## Sheet1
Feature List
Iteration | Feature | Implementation Started? | Asignee | Implementation Finished? | Relevant Classes
1 | Lesson Data Object | Yes | Alistair Jewers | Yes | Lesson.java
1 | Page Data Object | Yes | Alistair Jewers | Yes | Page.java
1 | Abstract Data Object | Yes | Alistair Jewers | Yes | PageObject.java
1 | Text Data Object | Yes | Daniel Berhe, Jake Ransom | Yes | TextObject.java
1 | Image Data Object | Yes | Sam Hall, Sam Raeburn | Yes | ImageObject.java
1 | Video Data Object | Yes | Alistair Jewers | Yes | VideoObject.java
1 | Audio Data Object | Yes | Sam Raeburn, Sam Hall | Yes | AudioObject.java
1 | Graphic Data Object | Yes | Lewis Thresh, Calum Armstrong | Yes | GrpahicObject.java
1 | Multiple Choice Data Object | Yes | Sam Hall, Sam Raeburn | Yes | MultipleChoiceObject.java, Answer.java
1 | Answer Box Data Object | Yes | Sam Raeburn, Sam Hall | Yes | AnswerBoxObject.java
1 | Lesson Metadata Objects | Yes | Alistair Jewers | Yes | LessonInfo.java, LessonDefaultSettings.java, LessonGradeSettings.java
1 | Parsing XML into data objects | Yes | Alistair Jewers | Yes | XMLParser.java
1 | Writing data objects to XML | Yes | Alistair Jewers | Yes | XMLWriter.java
1 | XML Handling | Yes | Alistair Jewers | Yes | XMLHandler.java
1 | Basic GUI to verify XML handling | Yes | Alistair Jewers | Yes | Iteration1DummyUI.java
2 | Image Handler | Yes | Daniel Berhe, Jake Ransom | Yes | ImageHandler.java
2 | Video Handler | Yes | Alistair Jewers | Yes | VideoHandler.java, Video.java
2 | Audio Handler | Yes | Alexander Cash, Calum Armstrong | Yes | AudioHandler.java, Audio.java
2 | Multiple Choice Handler | Yes | Emmanuel Olutayo, Penny Nicole | Yes | MultipleChoice.java, MultipleChoice.java, MChoiceCheckBox.java, MChoiceRadio.java
2 | Answer Box Handler | Yes | Daniel Berhe | Yes | AnswerBoxHandler.java, AnswerBox.java
2 | Lesson opening and closing | Yes | Alistair Jewers | Yes | RuntimeData.java
2 | Page selection, next and previous | Yes | Alistair Jewers | Yes | RuntimeData.java
2 | Render pages usng media handlers | Yes | Alistair Jewers | Yes | Renderer.java, Util.java
2 | Text Handler | Yes | WAVEMEDIA | Yes | WAVEMEDIA
2 | Graphics Handler | Yes | WAVEMEDIA | Yes | WAVEMEDIA
2 | Learn Easy GUI Framework | Yes | Sam Hall, Lewis Thresh | Yes | DummyGUILayout.java, LearnEasyClient.java
3, Learn Easy | Learn Easy Progress Tracking | Yes | Daniel Berhe, Sam Raeburn, Jake Ransom | Yes | RuntimeData.java
3, Learn Easy | Learn Easy Home Screen | Yes | Daniel Berhe | Yes | HomeScreen.java
3, Learn Easy | Learn Easy Certificate | Yes | Daniel Berhe, Alistair Jewers | Yes | CertificateWindow.java
3, Learn Easy | Learn Easy Extended File Opening (recents + local) | Yes | Daniel Berhe | Yes | RuntimeData.java
3, Learn Easy | Learn Easy Pause & Resume | No | Cancelled | Cancelled | N/A
3, Learn Easy | Support for marks and marking | Yes | Daniel Berhe, Sam Raeburn | Yes | ProgressTracker.java
3, GUI | Teach Easy GUI Framework | Yes | Sam Hall, Lewis Thresh | Yes | LearnEasyClient.java
3, GUI | Finalised Learn Easy GUI | Yes | Sam Hall, Lewis Thresh | Yes | LearnEasyClient.java
3, GUI | Finalised Teach Eay GUI | Yes | Sam Hall, Lewis Thresh | Yes | TeachEasyClient.java
3, Teach Easy | Editor page object adding and deletion | Yes | Alistair Jewers | Yes | EditorRuntimeData.java
3, Teach Easy | Editor page object selection | Yes | Alistair Jewers | Yes | EditorRuntimeData.java
3, Teach Easy | Editor page object manipulation | Yes | Alistair Jewers | Yes | EditorRuntimeData.java, PropertiesPane.java
3, Teach Easy | Editor Text Editing | Yes | Alistair Jewers | Yes | EditTextWindow.java, EditorRuntimeData.java
3, Teach Easy | Editor properties pane | Yes | Alistair Jewers, Lewis Thresh | Yes | EditorRuntimeData.java, TeachEasyClient.java, PropertiesPane.java
3, Teach Easy | Editor saving lessons | Yes | Alistair Jewers | Yes | RuntimeData.java
3, Teach Easy | Editor extra file handling (save as, recents...) | Cancelled | TBD | Cancelled | N/A
3, Teach Easy | Editor Preview Window | Yes | Alistair Jewers | Yes | PreviewWindow.java
3, Teach Easy | Editor Selected Object Highlighting | Yes | Emmanuel Olutayo, Alexander Cash | Yes | Renderer.java
3, Teach Easy | Page Templates / Categories | Yes | Penny Nicole, Calum Armstrong | Yes | TemplateController.java