## Sheet1
Meeting Matter Marked Complete
[5 empty] | Meeting: | 01 (QM1) | 02 (GM1) | 03 (QM2) | 04 (GM2) | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Action No. | Meeting Matter Arose | Date | Action | Person Responsible | Date: | 2015-01-19 | 2015-01-21 | 2015-01-26 | 2015-01-28
1 | 01 (Quick Meeting 1) | 2015-01-19 | Brainstorm Ideas for company name | ALL |  | Created | In Progress | In Progress | YES
2 | 01 (Quick Meeting 1) | 2015-01-19 | Consider age group for product | ALL |  | Created | In Progress | Yes
3 | 01 (Quick Meeting 1) | 2015-01-19 | Talk to Stuart about product idea | Alex |  | Created | YES
4 | 02 (General Meeting 1) | 2015-01-21 | Create Timesheet template | Sam R. |  |  | Created | YES
5 | 02 (General Meeting 1) | 2015-01-21 | Sign up to KanBan | Alex |  |  | Created | YES
6 | 02 (General Meeting 1) | 2015-01-21 | Set up Google Drive | Calum |  |  | Created | YES
7 | 02 (General Meeting 1) | 2015-01-21 | Set up Google Calandar | Lewis |  |  | Created | YES
8 | 02 (General Meeting 1) | 2015-01-21 | GitHub Demonstration | Alex, Ali |  |  | Created | YES
9 | 02 (General Meeting 1) | 2015-01-21 | Upload Example style file to Google Drive | Sam H. |  |  | Created | No | YES
10 | 02 (General Meeting 1) | 2015-01-21 | Select a coding style | Ali, Dan |  |  | Created | YES
11 | 02 (General Meeting 1) | 2015-01-21 | Email Stuart about week 4 hand in | Alex |  |  | Created | In Progress | YES
12 | 02 (General Meeting 1) | 2015-01-21 | Implement online poll for company name | Jake |  |  | Created | No | YES
13 | 03 (Quick Meeting 2) | 2015-01-26 | Register on GitHub | Calum |  |  |  | Created | YES
14 | 03 (Quick Meeting 2) | 2015-01-26 | GitHub push conflict | Alex |  |  |  | Created | In Progress | In Progress | YES
15 | 03 (Quick Meeting 2) | 2015-01-26 | Create Test Repository | Alex |  |  |  | Created | YES
16 | 03 (Quick Meeting 2) | 2015-01-26 | Write functional spec. | ALL |  |  |  | Created | In Progress | YES
17 | 03 (Quick Meeting 2) | 2015-01-26 | Email stuart about what is required for func. Spec. | Alex |  |  |  | Created | YES
18 | 03 (Quick Meeting 2) | 2015-01-26 | QA manual individual job role sections | ALL |  |  |  | Created | In Progress | In Progress | YES
19 | 03 (Quick Meeting 2) | 2015-01-26 | decide on company ethos / standards | ALL |  |  |  | Created | In Progress | In Progress | YES
20 | 03 (Quick Meeting 2) | 2015-01-26 | KanBan Invites | Alex |  |  |  | Created | YES
21 | 03 (Quick Meeting 2) | 2015-01-26 | Email Stuart about 3rd party software | Alex |  |  |  | Created | YES
22 | 03 (Quick Meeting 2) | 2015-01-26 | Email Stuart about bought code alterations | Alex |  |  |  | Created | YES
23 | 03 (Quick Meeting 2) | 2015-01-26 | Update Google Calender | Lewis |  |  |  | Created | YES
24 | 04 (GeneralMeeting 2) | 2015-01-28 | Write up functional spec. document | Alex |  |  |  |  | Created | In Progress | YES
25 | 04 (GeneralMeeting 2) | 2015-01-28 | Scan and upload example interfaces | Sam |  |  |  |  | Created | In Progress | YES
26 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Company profile and vision | Alex |  |  |  |  | Created | In Progress | YES
27 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Organizational structure | Emanuel |  |  |  |  | Created | In Progress | YES
28 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Deliverables | Calum |  |  |  |  | Created | In Progress | YES
29 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Project Management Methodology | Sam |  |  |  |  | Created | Canceled
30 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Requirements and Specifications phase | Ali |  |  |  |  | Created | Canceled
31 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Design phase | Sam |  |  |  |  | Created | Canceled
32 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Implementation phase | Jake |  |  |  |  | Created | Canceled
33 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Testing and integration phase | Sam R. |  |  |  |  | Created | Canceled
34 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Quality auditing reviews | Penny |  |  |  |  | Created | Canceled
35 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Sample questonair | Jake |  |  |  |  | Created | Canceled
36 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Code implementation example | Ali |  |  |  |  | Created | Canceled
37 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Class diagram | Ali |  |  |  |  | Created | Canceled
38 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: KanBan Example | Alex |  |  |  |  | Created | Canceled
39 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: GitHub progress tracking | Alex |  |  |  |  | Created | Canceled
40 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: GANTT Chart | Alex |  |  |  |  | Created | Canceled
41 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: QA metric list template | Dan |  |  |  |  | Created | Canceled
42 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Manager reports template | Dan |  |  |  |  | Created | Canceled
43 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Financial statement template | Emanuel, Penny |  |  |  |  | Created | Canceled
44 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Create google drive folder | Calum |  |  |  |  | Created | Canceled
45 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: General company document templates | Calum |  |  |  |  | Created | Canceled
46 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Collate parts | Lewis |  |  |  |  | Created | In Progress | YES
47 | 04 (GeneralMeeting 2) | 2015-01-28 | Except KanBan invites | ALL |  |  |  |  | Created | In Progress | YES
48 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Agile process diagram | Sam H. | [5 empty] | Created | YES
49 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Initial Requirements Capture | Ali | [5 empty] | Created | YES
50 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Project Plan | Jake | [5 empty] | Created | YES
51 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Itterative process | Sam R. | [5 empty] | Created | YES
52 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Pick user stories to implement | Ali | [5 empty] | Created | YES
53 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Design and planning phase | Lewis | [5 empty] | Created | YES
54 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Final product check | Penny | [5 empty] | Created | YES
55 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Quality assurance reviews | Dan | [5 empty] | Created | YES
56 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: General document | Calum | [5 empty] | Created | YES
57 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Minutes | Calum | [5 empty] | Created | YES
58 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Test reports | Sam R. | [5 empty] | Created | YES
59 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: GANTT Chart | Jake | [5 empty] | Created | YES
60 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: KanBan board | Jake | [5 empty] | Created | YES
61 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Timesheets | Calum | [5 empty] | Created | YES
62 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Weekly financial review | Emanuel | [5 empty] | Created | YES
63 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Contracts | Calum | [5 empty] | Created | YES
64 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Market research surveys | Jake | [5 empty] | Created | YES
65 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Review Document | Dan | [5 empty] | Created | YES
66 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Code templates | Ali | [5 empty] | Created | YES
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100