## Sheet1
Implementation Planning Spreadsheet
Iteration Timings
Iteration | Implementation Start | Implementation End
1 | Monday Week 4 , Spring Term | Monday Week 7, Spring Term
2 | Spring Week 7 | Summer Week 1
3 | Summer Week 1 | Summer Week 4
4 | Summer Week 4 | Summer Week 6
Feature List
Iteration | Feature | Implementation Started? | Asignee | Implementation Finished? | Relevant Classes
1 | Lesson Data Object | Yes | Alistair Jewers | Yes | Lesson.java
1 | Page Data Object | Yes | Alistair Jewers | Yes | Page.java
1 | Abstract Data Object | Yes | Alistair Jewers | Yes | PageObject.java
1 | Text Data Object | Yes | Daniel Berhe, Jake Ransom | Yes | TextObject.java
1 | Image Data Object | Yes | Sam Hall, Sam Raeburn | Yes | ImageObject.java
1 | Video Data Object | Yes | Alistair Jewers | Yes | VideoObject.java
1 | Audio Data Object | Yes | Sam Raeburn, Sam Hall | Yes | AudioObject.java
1 | Graphic Data Object | Yes | Lewis Thresh, Calum Armstrong | Yes | GrpahicObject.java
1 | Multiple Choice Data Object | Yes | Sam Hall, Sam Raeburn | Yes | MultipleChoiceObject.java, Answer.java
1 | Answer Box Data Object | Yes | Sam Raeburn, Sam Hall | Yes | AnswerBoxObject.java
1 | Lesson Metadata Objects | Yes | Alistair Jewers | Yes | LessonInfo.java, LessonDefaultSettings.java, LessonGradeSettings.java
1 | Parsing XML into data objects | Yes | Alistair Jewers | Yes | XMLParser.java
1 | Writing data objects to XML | Yes | Alistair Jewers | Yes | XMLWriter.java
1 | XML Handling | Yes | Alistair Jewers | Yes | XMLHandler.java
1 | Basic GUI to verify XML handling | Yes | Alistair Jewers | Yes | Iteration1DummyUI.java
2 | Image Handler | Yes | Daniel Berhe, Jake Ransom | Yes | ImageHandler.java
2 | Video Handler | Yes | Alistair Jewers | Yes | VideoHandler.java, Video.java
2 | Audio Handler | Yes | Alexander Cash, Calum Armstrong | Yes | AudioHandler.java, Audio.java
2 | Multiple Choice Handler | Yes | Emmanuel Olutayo, Penny Nicole | Yes | MultipleChoice.java, MultipleChoice.java, MChoiceCheckBox.java, MChoiceRadio.java
2 | Answer Box Handler | Yes | Daniel Berhe | Yes | AnswerBoxHandler.java, AnswerBox.java
2 | Lesson opening and closing | Yes | Alistair Jewers | Yes | RuntimeData.java
2 | Page selection, next and previous | Yes | Alistair Jewers | Yes | RuntimeData.java
2 | Render pages usng media handlers | Yes | Alistair Jewers | Yes | Renderer.java, Util.java
2 | Text Handler | Yes | WAVEMEDIA | Yes | WAVEMEDIA
2 | Graphics Handler | Yes | WAVEMEDIA | Yes | WAVEMEDIA
2 | Learn Easy GUI Framework | Yes | Sam Hall, Lewis Thresh | Yes | DummyGUILayout.java, LearnEasyClient.java
3, Learn Easy | Learn Easy Progress Tracking | No | On Hold | No | RuntimeData.java
3, Learn Easy | Learn Easy Home Screen | No | Daniel Berhe, Sam Raeburn, Jake Ransom | No
3, Learn Easy | Learn Easy Certificate | No | Daniel Berhe, Sam Raeburn, Jake Ransom | No
3, Learn Easy | Learn Easy Extended File Opening (recents) | No | Daniel Berhe, Sam Raeburn, Jake Ransom | No
3, Learn Easy | Learn Easy Pause & Resume | No | Daniel Berhe, Sam Raeburn, Jake Ransom | No
3, Learn Easy | Support for marks and marking | No | Daniel Berhe, Sam Raeburn, Jake Ransom | No
3, GUI | Teach Easy GUI Framework | Yes | Sam Hall, Lewis Thresh | No | LearnEasyClient.java
3, GUI | Finalised Learn Easy GUI | No | Sam Hall, Lewis Thresh | No | LearnEasyClient.java
3, GUI | Finalised Teach Eay GUI | No | Sam Hall, Lewis Thresh | No | TeachEasyClient.java
3, Teach Easy | Editor page object adding and deletion | Yes | Alistair Jewers | No | EditorRuntimeData.java
3, Teach Easy | Editor page object selection | Yes | Alistair Jewers | No | EditorRuntimeData.java
3, Teach Easy | Editor page object manipulation | Yes | Alistair Jewers | No | EditorRuntimeData.java, PropertiesPane.java
3, Teach Easy | Editor Text Editing | No | TBD
3, Teach Easy | Editor properties pane | Yes | Alistair Jewers, Lewis Thresh | No | EditorRuntimeData.java, TeachEasyClient.java, PropertiesPane.java
3, Teach Easy | Editor saving lessons | Yes | Alistair Jewers | No | RuntimeData.java
3, Teach Easy | Editor extra file handling (save as, recents...) | No | TBD
3, Teach Easy | Editor Preview Window? | No | TBD | No
3, Teach Easy | Editor Selected Object Highlighting | No | Emmanuel Olutayo, Alexander Cash | No | Renderer.java
3, Teach Easy | Page Templates / Categories | No | Penny Nicole, Calum Armstrong | No