## Action Tracking
Meeting Matter Marked Complete
[5 empty] | Meeting: | 01 (QM1) | 02 (GM1) | 03 (QM2) | 04 (GM2) | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Action No. | Meeting Matter Arose | Date | Action | Person Responsible | Date: | 2015-01-19 | 2015-01-21 | 2015-01-26 | 2015-01-28 | 2015-01-29 | 2015-02-02 | 2015-02-04 | 2015-02-06 | 2015-02-09 | 2015-02-11 | 2015-02-11 | 2015-02-18 | 2015-02-23 | 2015-02-25 | 2015-03-02 | 2015-03-04 | 2015-03-09 | 2015-03-11 | 2015-03-17 | 2015-04-13 | 2015-04-17 | 2015-04-20 | 2015-05-01 | 2015-05-04 | 2015-05-08 | 2015-05-18 | 2015-05-22 | 2015-05-25 | 2015-05-29 | End of Project
1 | 01 (Quick Meeting 1) | 2015-01-19 | Brainstorm Ideas for company name | ALL |  | Created | In Progress | In Progress | YES
2 | 01 (Quick Meeting 1) | 2015-01-19 | Consider age group for product | ALL |  | Created | In Progress | Yes
3 | 01 (Quick Meeting 1) | 2015-01-19 | Talk to Stuart about product idea | Alex |  | Created | YES
4 | 02 (General Meeting 1) | 2015-01-21 | Create Timesheet template | Sam R. |  |  | Created | YES
5 | 02 (General Meeting 1) | 2015-01-21 | Sign up to KanBan | Alex |  |  | Created | YES
6 | 02 (General Meeting 1) | 2015-01-21 | Set up Google Drive | Calum |  |  | Created | YES
7 | 02 (General Meeting 1) | 2015-01-21 | Set up Google Calandar | Lewis |  |  | Created | YES
8 | 02 (General Meeting 1) | 2015-01-21 | GitHub Demonstration | Alex, Ali |  |  | Created | YES
9 | 02 (General Meeting 1) | 2015-01-21 | Upload Example style file to Google Drive | Sam H. |  |  | Created | No | YES
10 | 02 (General Meeting 1) | 2015-01-21 | Select a coding style | Ali, Dan |  |  | Created | YES
11 | 02 (General Meeting 1) | 2015-01-21 | Email Stuart about week 4 hand in | Alex |  |  | Created | AR | YES
12 | 02 (General Meeting 1) | 2015-01-21 | Implement online poll for company name | Jake |  |  | Created | No | YES
13 | 03 (Quick Meeting 2) | 2015-01-26 | Register on GitHub | Calum |  |  |  | Created | YES
14 | 03 (Quick Meeting 2) | 2015-01-26 | GitHub push conflict | Alex |  |  |  | Created | In Progress | In Progress | YES
15 | 03 (Quick Meeting 2) | 2015-01-26 | Create Test Repository | Alex |  |  |  | Created | YES
16 | 03 (Quick Meeting 2) | 2015-01-26 | Write functional spec. | ALL |  |  |  | Created | In Progress | YES
17 | 03 (Quick Meeting 2) | 2015-01-26 | Email stuart about what is required for func. Spec. | Alex |  |  |  | Created | YES
18 | 03 (Quick Meeting 2) | 2015-01-26 | QA manual individual job role sections | ALL |  |  |  | Created | In Progress | In Progress | YES
19 | 03 (Quick Meeting 2) | 2015-01-26 | decide on company ethos / standards | ALL |  |  |  | Created | In Progress | In Progress | YES
20 | 03 (Quick Meeting 2) | 2015-01-26 | KanBan Invites | Alex |  |  |  | Created | YES
21 | 03 (Quick Meeting 2) | 2015-01-26 | Email Stuart about 3rd party software | Alex |  |  |  | Created | YES
22 | 03 (Quick Meeting 2) | 2015-01-26 | Email Stuart about bought code alterations | Alex |  |  |  | Created | YES
23 | 03 (Quick Meeting 2) | 2015-01-26 | Update Google Calender | Lewis |  |  |  | Created | YES
24 | 04 (GeneralMeeting 2) | 2015-01-28 | Write up functional spec. document | Alex |  |  |  |  | Created | In Progress | YES
25 | 04 (GeneralMeeting 2) | 2015-01-28 | Scan and upload example interfaces | Sam |  |  |  |  | Created | In Progress | YES
26 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Company profile and vision | Alex |  |  |  |  | Created | In Progress | YES
27 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Organizational structure | Emanuel |  |  |  |  | Created | In Progress | YES
28 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Deliverables | Calum |  |  |  |  | Created | In Progress | YES
29 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Project Management Methodology | Sam |  |  |  |  | Created | Canceled
30 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Requirements and Specifications phase | Ali |  |  |  |  | Created | Canceled
31 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Design phase | Sam |  |  |  |  | Created | Canceled
32 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Implementation phase | Jake |  |  |  |  | Created | Canceled
33 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Testing and integration phase | Sam R. |  |  |  |  | Created | Canceled
34 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Quality auditing reviews | Penny |  |  |  |  | Created | Canceled
35 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Sample questonair | Jake |  |  |  |  | Created | Canceled
36 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Code implementation example | Ali |  |  |  |  | Created | Canceled
37 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Class diagram | Ali |  |  |  |  | Created | Canceled
38 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: KanBan Example | Alex |  |  |  |  | Created | Canceled
39 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: GitHub progress tracking | Alex |  |  |  |  | Created | Canceled
40 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: GANTT Chart | Alex |  |  |  |  | Created | Canceled
41 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: QA metric list template | Dan |  |  |  |  | Created | Canceled
42 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Manager reports template | Dan |  |  |  |  | Created | Canceled
43 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Financial statement template | Emanuel, Penny |  |  |  |  | Created | Canceled
44 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Create google drive folder | Calum |  |  |  |  | Created | Canceled
45 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: General company document templates | Calum |  |  |  |  | Created | Canceled
46 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Collate parts | Lewis |  |  |  |  | Created | In Progress | YES
47 | 04 (GeneralMeeting 2) | 2015-01-28 | Except KanBan invites | ALL |  |  |  |  | Created | In Progress | YES
48 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Agile process diagram | Sam H. | [5 empty] | Created | YES
49 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Initial Requirements Capture | Ali | [5 empty] | Created | YES
50 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Project Plan | Jake | [5 empty] | Created | YES
51 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Itterative process | Sam R. | [5 empty] | Created | YES
52 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Pick user stories to implement | Ali | [5 empty] | Created | YES
53 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Design and planning phase | Lewis | [5 empty] | Created | YES
54 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Final product check | Penny | [5 empty] | Created | YES
55 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Quality assurance reviews | Dan | [5 empty] | Created | YES
56 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: General document | Calum | [5 empty] | Created | YES
57 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Minutes | Calum | [5 empty] | Created | YES
58 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Test reports | Sam R. | [5 empty] | Created | YES
59 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: GANTT Chart | Jake | [5 empty] | Created | YES
60 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: KanBan board | Jake | [5 empty] | Created | YES
61 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Timesheets | Calum | [5 empty] | Created | YES
62 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Weekly financial review | Emanuel | [5 empty] | Created | YES
63 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Contracts | Calum | [5 empty] | Created | YES
64 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Market research surveys | Jake | [5 empty] | Created | YES
65 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Review Document | Dan | [5 empty] | Created | YES
66 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Code templates | Ali | [5 empty] | Created | YES
67 | 06 (Quick Meeting 3) | 2015-02-02 | Timesheets to be filled in and handed to Calum | ALL | [6 empty] | Created | YES
68 | 06 (Quick Meeting 3) | 2015-02-02 | Email Stuart about PWS | Alex | [6 empty] | Created | AR | N/A | YES
69 | 06 (Quick Meeting 3) | 2015-02-02 | Email stuart about employee wages | Alex | [6 empty] | Created | AR | N/A | YES
70 | 06 (Quick Meeting 3) | 2015-02-02 | Arange meeting to discuss financial plan | Penny, Emanuel | [6 empty] | Created | YES
71 | 07 (Planning Meeting 1) | 2015-02-04 | Arange inter-group PWS meeting | Alex, Calum | [7 empty] | Created | YES
72 | 07 (Planning Meeting 1) | 2015-02-04 | Write abstract object class | Ali | [7 empty] | Created | N/A | YES
73 | 07 (Planning Meeting 1) | 2015-02-04 | Define tasts to begin paired programming | Alex, Ali | [7 empty] | Created | N/A | YES
74 | 07 (Planning Meeting 1) | 2015-02-04 | Create project in dev. Repository | Ali | [7 empty] | Created | N/A | YES
75 | 08 (PWS briefing) | 2015-02-06 | NO ACTIONS MADE | N/A | [8 empty] | N/A | N/A
76 | 09 (Quick Meeting 4) | 2015-02-09 | Issue tagging and branch pushing demonstration | Ali | [9 empty] | Created | In Progress | N/A | YES
77 | 09 (Quick Meeting 4) | 2015-02-09 | Hand in completed timesheets | Alex, Dan, Sam H., Jake | [9 empty] | Created | YES
78 | 09 (Quick Meeting 4) | 2015-02-09 | Brainstorm ideas for Tender Presentation | ALL | [9 empty] | Created | YES
79 | 10 (Tender Presentation Meeting) | 2015-02-11 | Teach Easy and Learn Easy UI Design | Sam H. | [10 empty] | Created | N/A | YES
80 | 10 (Tender Presentation Meeting) | 2015-02-11 | Logos finalised | Lewis | [10 empty] | Created | N/A | YES
81 | 10 (Tender Presentation Meeting) | 2015-02-11 | Teacher market research ethics form | Jake | [10 empty] | Created | N/A | YES
82 | 10 (Tender Presentation Meeting) | 2015-02-11 | Student market research ethics form | Sam | [10 empty] | Created | N/A | YES
83 | 10 (Tender Presentation Meeting) | 2015-02-11 | Presentation drafts | ALL | [10 empty] | Created | N/A | YES
84 | 11 (PWS Agrement Meeting) | 2015-02-11 | NO ACTIONS MADE | N/A | [11 empty] | N/A | N/A
85 | 12 (General Meeting 3) | 2015-02-18 | Define term "bug" in contract | Calum | [12 empty] | Created | N/A | YES
86 | 12 (General Meeting 3) | 2015-02-18 | Alter contract to allow for code edditing | Calum | [12 empty] | Created | N/A | YES
87 | 12 (General Meeting 3) | 2015-02-18 | Alter contract with regards to bug compansation | Calum | [12 empty] | Created | N/A | YES
88 | 12 (General Meeting 3) | 2015-02-18 | Alther contract to include code transfer deadline | Calum | [12 empty] | Created | N/A | YES
89 | 12 (General Meeting 3) | 2015-02-18 | Redesign timesheets to include justifications | Calum | [12 empty] | Created | N/A | YES
90 | 13 (Quick Meeting 5) | 2015-02-23 | Create plan for coding | Alex | [13 empty] | Created | In Progress | YES
91 | 13 (Quick Meeting 5) | 2015-02-23 | Fill in time predictions | ALL | [13 empty] | Created | In Progress | YES
92 | 13 (Quick Meeting 5) | 2015-02-23 | Work with Wave Media to finish contracts | Calum | [13 empty] | Created | YES
93 | 14 (General Meeting 4) | 2015-02-25 | Compose email to staurt re: presentation feedback | Alex | [14 empty] | Created | In Progress | AR | AR | AR | N/A | See 137.
94 | 15 (Quick Meeting 6) | 2015-03-02 | Begin work with Alex on audio handler | Calum | [15 empty] | Created | No | YES
95 | 15 (Quick Meeting 6) | 2015-03-02 | Test Video Handler | Sam R. | [15 empty] | Created | In Progress | YES
96 | 15 (Quick Meeting 6) | 2015-03-02 | Fill in category specific working hours online | Calum | [15 empty] | Created | YES
97 | 16 (General Meeting 5) | 2015-03-04 | Draft spreadsheet to re-apply for loan | Emmanuel, Penny | [16 empty] | Created | In Progress | YES
98 | 16 (General Meeting 5) | 2015-03-04 | Track down Sam H. timesheet for financial report | Calum, Alex | [16 empty] | Created | YES
99 | 16 (General Meeting 5) | 2015-03-04 | Alter user stories to better fit release specifications | Alex | [16 empty] | Created | In Progress | YES
100 | 16 (General Meeting 5) | 2015-03-04 | Translate release plan to KanBan tasks | Alex | [16 empty] | Created | No | No | N/A | Cancelled
101 | 16 (General Meeting 5) | 2015-03-04 | Look into .ogg and .m4a support without javaFX | Alex, Calum | [16 empty] | Created | No | In Progress | N/A | YES
102 | 17 (Quick Meeting 7) | 2015-03-09 | Implement a more up to date GUI | Sam H. | [17 empty] | Created | YES
103 | 17 (Quick Meeting 7) | 2015-03-09 | Implement looping feaure in audio handler | Calum, Alex | [17 empty] | Created | In Progress | N/A | YES
104 | 17 (Quick Meeting 7) | 2015-03-09 | Create standard media handler test file | Ali | [17 empty] | Created | YES
105 | 17 (Quick Meeting 7) | 2015-03-09 | Complete and file all test reports for first iteration | ALL | [17 empty] | Created | In Progress | N/A | YES
106 | 17 (Quick Meeting 7) | 2015-03-09 | Discuss Presentation at supervisions | ALL | [17 empty] | Created | YES
107 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Look into full screen video scanning | Ali | [18 empty] | Created | N/A | YES
108 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Rectify fails on test reports | ALL | [18 empty] | Created | N/A | YES
109 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Test Image handler | Alex | [18 empty] | Created | N/A | YES
110 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Prepare tests for Text and Graphics Handlers | Sam R. | [18 empty] | Created | N/A | YES
111 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Collate previous tasts from minutes | Calum | [18 empty] | Created | N/A | In Progress | YES
112 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Arange planning meeting for Week 1, Summer term | Alex | [18 empty] | Created | N/A | No
113 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Break down blocks in software summary diagram | Ali | [18 empty] | Created | N/A | YES
114 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Implement warning / error pop up windows | Ali | [18 empty] | Created | N/A | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | YES
115 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Design student certificate | Sam H., Lewis | [18 empty] | Created | N/A | YES
116 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Test renderer | Sam R. | [18 empty] | Created | N/A | No | No | No | No | No | No | No | In Progress | In Progress | YES
117 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Test runtime | Sam R. | [18 empty] | Created | N/A | No | No | No | No | No | No | No | In Progress | In Progress | YES
118 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Email Tony Ward about selling stagegies | Alex | [18 empty] | Created | N/A | YES
119 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Produce GUI survey | Jake | [18 empty] | Created | N/A | No | No | No | No | No | No | No | Cancelled
120 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Look into brand awareness / sofia selling points | Jake | [18 empty] | Created | N/A | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | YES
121 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Look into YouTube streaming | Alex | [18 empty] | Created | N/A | YES
122 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Reformat XML | Ali | [18 empty] | Created | N/A | YES
123 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Look into object timing support | Ali | [18 empty] | Created | N/A | YES
124 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Write Finance summary | Emmanuel, Penny | [18 empty] | Created | N/A | YES
125 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Write Marketing summary | Jake | [18 empty] | Created | N/A | YES
126 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Complete individual QA Metric reports | ALL | [18 empty] | Created | N/A | YES
127 | 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | Ensure interation 1 documents are compiled | Alex | [18 empty] | Created | N/A | YES
128 | 19 (UK Software Integration Meeting) | 2015-03-17 | Compile list of properties pane properties | Lewis | [19 empty] | Created | YES
129 | 19 (UK Software Integration Meeting) | 2015-03-17 | Compile list of sale module's graphical ellements | Ali | [19 empty] | Created | YES
130 | 19 (UK Software Integration Meeting) | 2015-03-17 | Define home screen content, and funtion | Dan | [19 empty] | Created | YES
131 | 19 (UK Software Integration Meeting) | 2015-03-17 | Design home screen interface | Sam H., Lewis | [19 empty] | Created | YES
132 | 19 (UK Software Integration Meeting) | 2015-03-17 | Merge current UI branch | Lewis | [19 empty] | Created | YES
133 | 19 (UK Software Integration Meeting) | 2015-03-17 | Create new UI branch | Lewis | [19 empty] | Created | YES
134 | 20 (Quick Meeting 8) | 2015-04-13 | Alter contract to remove file sormat support | Calum | [20 empty] | Created | In Progress | YES
135 | 20 (Quick Meeting 8) | 2015-04-13 | Co-ordinate retesting of media handlers | Sam R. | [20 empty] | Created | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | YES
136 | 20 (Quick Meeting 8) | 2015-04-13 | Finish Audio Handler | Alex | [20 empty] | Created | YES
137 | 20 (Quick Meeting 8) | 2015-04-13 | Re-Email Stuart re: Presentation Concerns | Alex | [20 empty] | Created | AR | AR | AR | AR | AR | AR | AR | See 137.
138 | 21 (General Meeting 7) | 2015-04-17 | Request survey responses | ALL | [21 empty] | Created | In Progress | In Progress | In Progress | In Progress | In Progress | YES
139 | 22 (Quick Meeting 9) | 2015-04-20 | Distribute parser and bought code test cases | Sam R. | [22 empty] | Created | No | No | No | No | In Progress | In Progress | YES
140 | 22 (Quick Meeting 9) | 2015-04-20 | Arrange meeting with Wave Media re: Contracts | Alex, Calum | [22 empty] | Created | YES
141 | 23 (General Meeting 8) | 2015-05-01 | Implement feature - templates only for a new page | Calum, Penny, Ali | [23 empty] | Created | No | No | No | No | No | In Progress | YES
142 | 23 (General Meeting 8) | 2015-05-01 | Brainstorm ideas for sales presentation | ALL | [23 empty] | Created | In Progress | YES
143 | 24 (Quick Meeting 10) | 2015-05-04 | Arrange meeting to agree on meeting times | Alex, Calum | [24 empty] | Created | YES
144 | 24 (Quick Meeting 10) | 2015-05-04 | Email Greg Hunt about screen capture software | Alex | [24 empty] | Created | AR | AR | AR | AR | Cancelled
145 | 24 (Quick Meeting 10) | 2015-05-04 | Email Tony Ward about financial report deadline | Emmanuel | [24 empty] | Created | AR | YES
146 | 25 (General Meeting 9) | 2015-05-08 | Look into KeyGen outsourcing pricing | Calum, Lewis | [25 empty] | Created | No | No | No | Cancelled
147 | 25 (General Meeting 9) | 2015-05-08 | Add identifier question to marketing survey | Alex | [25 empty] | Created | YES
148 | 25 (General Meeting 9) | 2015-05-08 | Complete marketing report | Jake | [25 empty] | Created | YES
149 | 25 (General Meeting 9) | 2015-05-08 | Begin collating documentation from 15/05/15 | Calum | [25 empty] | Created | YES
150 | 25 (General Meeting 9) | 2015-05-08 | Email Stuart about timing functionality | Ali | [25 empty] | Created | YES
151 | 26 (Sales Presentation Meeting) | 2015-05-18 | NO ACTIONS MADE | N/A | [26 empty] | N/A | N/A
152 | 27 (General Meeting 10) | 2015-05-22 | Send email regarding Tender Presentation Feedback | Alex | [27 empty] | Created | No | AR | AR
153 | 27 (General Meeting 10) | 2015-05-22 | Submit all backdated timesheets | ALL | [27 empty] | Created | In Progress | YES
154 | 27 (General Meeting 10) | 2015-05-22 | Meeting regarding product pricing | Jake, Emmanuel, Penny | [27 empty] | Created | Cancelled
155 | 27 (General Meeting 10) | 2015-05-22 | Look into fixing page swapping bug | Dan, Ali | [27 empty] | Created | In Progress | YES
156 | 27 (General Meeting 10) | 2015-05-22 | Rectify all test report fails | ALL | [27 empty] | Created | In Progress | In Progress | Cancelled
157 | 28 (Quick Meeting 11) | 2015-05-25 | Work to create certificate | Dan, Lewis | [28 empty] | Created | YES
158 | 29 (General Meeting 11) | 2015-05-29 | Multiple choice boundry boxes | Alex | [29 empty] | Created | YES
159 | 29 (General Meeting 11) | 2015-05-29 | Audio Handler refactoring | Alex | [29 empty] | Created | YES
160 | 29 (General Meeting 11) | 2015-05-29 | Audio handler boundry boxes | Alex | [29 empty] | Created | YES
161 | 29 (General Meeting 11) | 2015-05-29 | Video handler bug | Ali | [29 empty] | Created | YES
162 | 29 (General Meeting 11) | 2015-05-29 | Template integration | Ali | [29 empty] | Created | YES
163 | 29 (General Meeting 11) | 2015-05-29 | Organize general commenting / refactoring | Ali | [29 empty] | Created | YES
164 | 29 (General Meeting 11) | 2015-05-29 | write presentation introduction / outro | Alex | [29 empty] | Created | YES
165 | 29 (General Meeting 11) | 2015-05-29 | Insert graphs for interactive media in presentation | Dan | [29 empty] | Created | YES
166 | 29 (General Meeting 11) | 2015-05-29 | Product intro | Sam R. | [29 empty] | Created | YES
167 | 29 (General Meeting 11) | 2015-05-29 | Product demo | Ali, Sam R. | [29 empty] | Created | YES
168 | 29 (General Meeting 11) | 2015-05-29 | Future development | Alex | [29 empty] | Created | YES
169 | 29 (General Meeting 11) | 2015-05-29 | Presentation extras / handouts | Calum | [29 empty] | Created | YES
170 | 29 (General Meeting 11) | 2015-05-29 | Question preperation | Lewis | [29 empty] | Created | YES
171 | 29 (General Meeting 11) | 2015-05-29 | Financial Figures justifications | Lewis | [29 empty] | Created | YES
End of Project
| Action being implemented | AR | Awaiting Reply (Emails)
Action Completed
Action is yet to be implemented, but is still active
Action has ceased to be active

## Register
Week | Meeting | Date | Length (Hrs) | Attendance | [9 empty] | Reasons for absense
|  |  |  | Alex Cash | Calum Armstrong | Daniel Berhe | Sam Hall | Alistair Jewers | Penelope Nichole | Emmanuel Olutayo | Samuel Raeburn | Jake Ransome | Lewis Thresh
19th Jan | 01 (Quick Meeting 1) | 2015-01-19 | 1 | y | y | y | y | y | y | y | y | n | y
| 02 (General Meeting 1) | 2015-01-21 | 3 | y | y | y | y | y | y | y | y | y | y
26th Jan | 03 (Quick Meeting 2) | 2015-01-26 | 0.75 | y | y | y | y | y | y | y | y | n | y
| 04 (General Meeting 2) | 2015-01-28 | 3 | y | y | y | y | y | y | y | y | y | y
| 05 (QA Manual Meeting) | 2015-01-29 | 2 | y | y | y | y | y | y | y | y | y | y
02nd Feb | 06 (Quick Meeting 3) | 2015-02-02 | 1 | y | y | y | y | y | y | y | y | n | y
| 07 (Planning Meeting 1) | 2015-02-04 | 3 | y | y | y | y | y | y | y | y | y | n
| 08 (PWS Briefing) | 2015-02-06 | 1 |  | y |  |  | y
09th Feb | 09 (Quick Meeting 4) | 2015-02-09 | 0.75 | y | y | y | y | y | y | y | y | n | y
| 10 (Tender Presentation Meeting) | 2015-02-11 | 1.75 | y | y | y | y | y | y | y | y | y | y
| 11 (PWS Agreement Meeting) | 2015-02-11 | 3 | y | y |  |  | y
16th Feb | 12 (General Meeting 3) | 2015-02-18 | 3 | y | y | y | y | y | y | y | y | y | y
23rd Feb | 13 (Quick Meeting 5) | 2015-02-23 | 1 | y | n | y | y | y | y | n | n | n | y
| 14 (General Meeting 4) | 2015-02-25 | 1.75 | y | y | y | y | y | y | y | y | y | y
02nd Mar | 15 (Quick Meeting 6) | 2015-03-02 | 1 | y | y | n | y | y | y | y | y | n | y
| 16 (General Meeting 5) | 2015-03-04 | 2 | y | y | y | n | y | y | y | y | y | y
09th Mar | 17 (Quick Meeting 7) | 2015-03-09 | 0.5 | y | y | y | y | y | y | y | y | y | y
| 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | 1.75 | y | y | y |  | y | y | y | y | y | y
16th Mar | 19 (UX Software Integration Meeting) | 2015-03-17 | 1 |  |  | y | n | y |  |  |  |  | y
23rd Mar | No Meetings (Easter 2)
30th Mar | No Meetings (Easter 3)
6th Apr | No Meetings (Easter 4)
13th Apr | 20 (Quick Meeting 8) | 2015-04-13 | 0.5 | y | y | y | n | y | y | y | y | n | y
| 21 (General Meeting 7) | 2015-04-17 | 1 | y | y | y | y | y | y | y | y | y | y
20th Apr | 22 (Quick Meeting 9) | 2015-04-20 | 0.5 | y | n | y | y | y | y | y | y | n | y
27th Apr | 23 (General Meeting 8) | 2015-05-01 | 0.75 | y | y | y | y | y | y | y | y | n | y
4th May | 24 (Quick Meeting 10) | 2015-05-04 | 0.5 | y | y | n | n | y | y | y | y | n | y
| 25 (General Meeting 9) | 2015-05-08 | 1 | y | y | y | y | y | y | y | y | y | y
11th May | No Meetings
18th May | 26 (Sales Presentation Meeting) | 2015-05-18 | 1 | y | y | y | y | y | y | y | y | y | y
| 27 (General Meeting 10) | 2015-05-22 | 1.5 | y | y | y | y | y | n | n | y | y | y
25th May | 28 (Quick Meting 11) | 2015-05-25 | 0.5 | y | n | y | y | y | y | y | y | n | y
| 29 (General Meeting 11) | 2015-05-29 | 1.5 | y | y | y | y | y | y | n | y | y | y
Not expected at meeting
Present
Absent
No Meetings that week

## Absence notes
Week | Meeting | Date | Length (Hrs) | Attendance
|  |  |  | Alex Cash | Calum Armstrong | Daniel Berhe | Sam Hall | Alistair Jewers | Penelope Nichole | Emmanuel Olutayo | Samuel Raeburn | Jake Ransome | Lewis Thresh
19th Jan | 01 (Quick Meeting 1) | 2015-01-19 | 1 | [8 empty] | None
| 02 (General Meeting 1) | 2015-01-21 | 3
26th Jan | 03 (Quick Meeting 2) | 2015-01-26 | 0.75 | [8 empty] | None
| 04 (General Meeting 2) | 2015-01-28 | 3
| 05 (QA Manual Meeting) | 2015-01-29 | 2
02nd Feb | 06 (Quick Meeting 3) | 2015-02-02 | 1 | [8 empty] | Not aware of meeting
| 07 (Planning Meeting 1) | 2015-02-04 | 3 | [9 empty] | Another meeting to atttend
| 08 (PWS Briefing) | 2015-02-06 | 1
09th Feb | 09 (Quick Meeting 4) | 2015-02-09 | 0.75 | [8 empty] | Family Arangements
| 10 (Tender Presentation Meeting) | 2015-02-11 | 1.75
| 11 (PWS Agreement Meeting) | 2015-02-11 | 3
16th Feb | 12 (General Meeting 3) | 2015-02-18 | 3
23rd Feb | 13 (Quick Meeting 5) | 2015-02-23 | 1 |  | Conflicting Contracts Meeting |  |  |  |  | UBF | Funeral | Family Responsibilities
| 14 (General Meeting 4) | 2015-02-25 | 1.75
02nd Mar | 15 (Quick Meeting 6) | 2015-03-02 | 1 |  |  | Unknown but Forewarned | [5 empty] | Over-tired due to late night
| 16 (General Meeting 5) | 2015-03-04 | 2 |  |  |  | Conflicting Event
09th Mar | 17 (Quick Meeting 7) | 2015-03-09 | 0.5
| 18 (General Meeting 6 and Product Demonstration) | 2015-03-11 | 1.75
16th Mar | 19 (UX Software Integration Meeting) | 2015-03-17 | 1 |  |  |  | UBF
23rd Mar | No Meetings (Easter 2)
30th Mar | No Meetings (Easter 3)
6th Apr | No Meetings (Easter 4)
13th Apr | 20 (Quick Meeting 8) | 2015-04-13 | 0.5 |  |  |  | Not in York |  |  |  |  | Unavailable due to car MOT
| 21 (General Meeting 7) | 2015-04-17 | 1
20th Apr | 22 (Quick Meeting 9) | 2015-04-20 | 0.5 |  | Unavailable due to placement interview | [6 empty] | Car MOT
27th Apr | 23 (General Meeting 8) | 2015-05-01 | 0.75
4th May | 24 (Quick Meeting 10) | 2015-05-04 | 0.5 |  |  | Unknown but Forewarned | Unknown but Forewarned |  |  |  |  | In Sheffield
| 25 (General Meeting 9) | 2015-05-08 | 1
11th May | No Meetings
18th May | 26 (Sales Presentation Meeting) | 2015-05-18
| 27 (General Meeting 10) | 2015-05-22 | [6 empty] | Revising for exam | Revising for exam
25th May | 28 (Quick Meting 11) | 2015-05-25 | 0.5 |  | Booked time away | [6 empty] | Up until 5:30 AM
| 29 (General Meeting 11) | 2015-05-29 | 1.5 | [6 empty] | Family Circumstances