## Sheet1
Meeting Matter Marked Complete
[5 empty] | Meeting: | 01 (QM1) | 02 (GM1) | 03 (QM2) | 04 (GM2) | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Action No. | Meeting Matter Arose | Date | Action | Person Responsible | Date: | 2015-01-19 | 2015-01-21 | 2015-01-26 | 2015-01-28 | 2015-01-29 | 2015-02-02 | 2015-02-04 | 2015-02-06 | 2015-02-09 | 2015-02-11 | 2015-02-11 | 2015-02-18 | 2015-02-23 | 2015-02-25 | 2015-03-02 | 2015-03-04
1 | 01 (Quick Meeting 1) | 2015-01-19 | Brainstorm Ideas for company name | ALL |  | Created | In Progress | In Progress | YES
2 | 01 (Quick Meeting 1) | 2015-01-19 | Consider age group for product | ALL |  | Created | In Progress | Yes
3 | 01 (Quick Meeting 1) | 2015-01-19 | Talk to Stuart about product idea | Alex |  | Created | YES
4 | 02 (General Meeting 1) | 2015-01-21 | Create Timesheet template | Sam R. |  |  | Created | YES
5 | 02 (General Meeting 1) | 2015-01-21 | Sign up to KanBan | Alex |  |  | Created | YES
6 | 02 (General Meeting 1) | 2015-01-21 | Set up Google Drive | Calum |  |  | Created | YES
7 | 02 (General Meeting 1) | 2015-01-21 | Set up Google Calandar | Lewis |  |  | Created | YES
8 | 02 (General Meeting 1) | 2015-01-21 | GitHub Demonstration | Alex, Ali |  |  | Created | YES
9 | 02 (General Meeting 1) | 2015-01-21 | Upload Example style file to Google Drive | Sam H. |  |  | Created | No | YES
10 | 02 (General Meeting 1) | 2015-01-21 | Select a coding style | Ali, Dan |  |  | Created | YES
11 | 02 (General Meeting 1) | 2015-01-21 | Email Stuart about week 4 hand in | Alex |  |  | Created | AR | YES
12 | 02 (General Meeting 1) | 2015-01-21 | Implement online poll for company name | Jake |  |  | Created | No | YES
13 | 03 (Quick Meeting 2) | 2015-01-26 | Register on GitHub | Calum |  |  |  | Created | YES
14 | 03 (Quick Meeting 2) | 2015-01-26 | GitHub push conflict | Alex |  |  |  | Created | In Progress | In Progress | YES
15 | 03 (Quick Meeting 2) | 2015-01-26 | Create Test Repository | Alex |  |  |  | Created | YES
16 | 03 (Quick Meeting 2) | 2015-01-26 | Write functional spec. | ALL |  |  |  | Created | In Progress | YES
17 | 03 (Quick Meeting 2) | 2015-01-26 | Email stuart about what is required for func. Spec. | Alex |  |  |  | Created | YES
18 | 03 (Quick Meeting 2) | 2015-01-26 | QA manual individual job role sections | ALL |  |  |  | Created | In Progress | In Progress | YES
19 | 03 (Quick Meeting 2) | 2015-01-26 | decide on company ethos / standards | ALL |  |  |  | Created | In Progress | In Progress | YES
20 | 03 (Quick Meeting 2) | 2015-01-26 | KanBan Invites | Alex |  |  |  | Created | YES
21 | 03 (Quick Meeting 2) | 2015-01-26 | Email Stuart about 3rd party software | Alex |  |  |  | Created | YES
22 | 03 (Quick Meeting 2) | 2015-01-26 | Email Stuart about bought code alterations | Alex |  |  |  | Created | YES
23 | 03 (Quick Meeting 2) | 2015-01-26 | Update Google Calender | Lewis |  |  |  | Created | YES
24 | 04 (GeneralMeeting 2) | 2015-01-28 | Write up functional spec. document | Alex |  |  |  |  | Created | In Progress | YES
25 | 04 (GeneralMeeting 2) | 2015-01-28 | Scan and upload example interfaces | Sam |  |  |  |  | Created | In Progress | YES
26 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Company profile and vision | Alex |  |  |  |  | Created | In Progress | YES
27 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Organizational structure | Emanuel |  |  |  |  | Created | In Progress | YES
28 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Deliverables | Calum |  |  |  |  | Created | In Progress | YES
29 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Project Management Methodology | Sam |  |  |  |  | Created | Canceled
30 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Requirements and Specifications phase | Ali |  |  |  |  | Created | Canceled
31 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Design phase | Sam |  |  |  |  | Created | Canceled
32 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Implementation phase | Jake |  |  |  |  | Created | Canceled
33 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Testing and integration phase | Sam R. |  |  |  |  | Created | Canceled
34 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Quality auditing reviews | Penny |  |  |  |  | Created | Canceled
35 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Sample questonair | Jake |  |  |  |  | Created | Canceled
36 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Code implementation example | Ali |  |  |  |  | Created | Canceled
37 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Class diagram | Ali |  |  |  |  | Created | Canceled
38 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: KanBan Example | Alex |  |  |  |  | Created | Canceled
39 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: GitHub progress tracking | Alex |  |  |  |  | Created | Canceled
40 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: GANTT Chart | Alex |  |  |  |  | Created | Canceled
41 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: QA metric list template | Dan |  |  |  |  | Created | Canceled
42 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Manager reports template | Dan |  |  |  |  | Created | Canceled
43 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Financial statement template | Emanuel, Penny |  |  |  |  | Created | Canceled
44 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Create google drive folder | Calum |  |  |  |  | Created | Canceled
45 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: General company document templates | Calum |  |  |  |  | Created | Canceled
46 | 04 (GeneralMeeting 2) | 2015-01-28 | QA: Collate parts | Lewis |  |  |  |  | Created | In Progress | YES
47 | 04 (GeneralMeeting 2) | 2015-01-28 | Except KanBan invites | ALL |  |  |  |  | Created | In Progress | YES
48 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Agile process diagram | Sam H. | [5 empty] | Created | YES
49 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Initial Requirements Capture | Ali | [5 empty] | Created | YES
50 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Project Plan | Jake | [5 empty] | Created | YES
51 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Itterative process | Sam R. | [5 empty] | Created | YES
52 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Pick user stories to implement | Ali | [5 empty] | Created | YES
53 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Design and planning phase | Lewis | [5 empty] | Created | YES
54 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Final product check | Penny | [5 empty] | Created | YES
55 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Quality assurance reviews | Dan | [5 empty] | Created | YES
56 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: General document | Calum | [5 empty] | Created | YES
57 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Minutes | Calum | [5 empty] | Created | YES
58 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Test reports | Sam R. | [5 empty] | Created | YES
59 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: GANTT Chart | Jake | [5 empty] | Created | YES
60 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: KanBan board | Jake | [5 empty] | Created | YES
61 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Timesheets | Calum | [5 empty] | Created | YES
62 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Weekly financial review | Emanuel | [5 empty] | Created | YES
63 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Contracts | Calum | [5 empty] | Created | YES
64 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Market research surveys | Jake | [5 empty] | Created | YES
65 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Document Template: Review Document | Dan | [5 empty] | Created | YES
66 | 05 (QA Manual Meeting) | 2015-01-29 | QA: Code templates | Ali | [5 empty] | Created | YES
67 | 06 (Quick Meeting 3) | 2015-02-02 | Timesheets to be filled in and handed to Calum | ALL | [6 empty] | Created | YES
68 | 06 (Quick Meeting 3) | 2015-02-02 | Email Stuart about PWS | Alex | [6 empty] | Created | AR | N/A | YES
69 | 06 (Quick Meeting 3) | 2015-02-02 | Email stuart about employee wages | Alex | [6 empty] | Created | AR | N/A | YES
70 | 06 (Quick Meeting 3) | 2015-02-02 | Arange meeting to discuss financial plan | Penny, Emanuel | [6 empty] | Created | YES
71 | 07 (Planning Meeting 1) | 2015-02-04 | Arange inter-group PWS meeting | Alex, Calum | [7 empty] | Created | YES
72 | 07 (Planning Meeting 1) | 2015-02-04 | Write abstract object class | Ali | [7 empty] | Created | N/A | YES
73 | 07 (Planning Meeting 1) | 2015-02-04 | Define tasts to begin paired programming | Alex, Ali | [7 empty] | Created | N/A | YES
74 | 07 (Planning Meeting 1) | 2015-02-04 | Create project in dev. Repository | Ali | [7 empty] | Created | N/A | YES
75 | 08 (PWS briefing) | 2015-02-06 | NO ACTIONS MADE | N/A | [8 empty] | N/A | N/A
76 | 09 (Quick Meeting 4) | 2015-02-09 | Issue tagging and branch pushing demonstration | Ali | [9 empty] | Created | In Progress | N/A | YES
77 | 09 (Quick Meeting 4) | 2015-02-09 | Hand in completed timesheets | Alex, Dan, Sam H., Jake | [9 empty] | Created | YES
78 | 09 (Quick Meeting 4) | 2015-02-09 | Brainstorm ideas for Tender Presentation | ALL | [9 empty] | Created | YES
79 | 10 (Tender Presentation Meeting) | 2015-02-11 | Teach Easy and Learn Easy UI Design | Sam H. | [10 empty] | Created | N/A | YES
80 | 10 (Tender Presentation Meeting) | 2015-02-11 | Logos finalised | Lewis | [10 empty] | Created | N/A | YES
81 | 10 (Tender Presentation Meeting) | 2015-02-11 | Teacher market research ethics form | Jake | [10 empty] | Created | N/A | YES
82 | 10 (Tender Presentation Meeting) | 2015-02-11 | Student market research ethics form | Sam | [10 empty] | Created | N/A | YES
83 | 10 (Tender Presentation Meeting) | 2015-02-11 | Presentation drafts | ALL | [10 empty] | Created | N/A | YES
84 | 11 (PWS Agrement Meeting) | 2015-02-11 | NO ACTIONS MADE | N/A | [11 empty] | N/A | N/A
85 | 12 (General Meeting 3) | 2015-02-18 | Define term "bug" in contract | Calum | [12 empty] | Created | N/A | YES
86 | 12 (General Meeting 3) | 2015-02-18 | Alter contract to allow for code edditing | Calum | [12 empty] | Created | N/A | YES
87 | 12 (General Meeting 3) | 2015-02-18 | Alter contract with regards to bug compansation | Calum | [12 empty] | Created | N/A | YES
| 12 (General Meeting 3) | 2015-02-18 | Alther contract to include code transfer deadline | Calum | [12 empty] | Created | N/A | YES
88 | 12 (General Meeting 3) | 2015-02-18 | Redesign timesheets to include justifications | Calum | [12 empty] | Created | N/A | YES
89 | 13 (Quick Meeting 5) | 2015-02-23 | Create plan for coding | Alex | [13 empty] | Created | In Progress | YES
90 | 13 (Quick Meeting 5) | 2015-02-23 | Fill in time predictions | ALL | [13 empty] | Created | In Progress | Yes
91 | 13 (Quick Meeting 5) | 2015-02-23 | Work with Wave Media to finish contracts | Calum | [13 empty] | Created | YES
92 | 14 (General Meeting 4) | 2015-02-25 | Compose email to staurt re: presentation feedback | Alex | [14 empty] | Created | In Progress | AR
93 | 15 (Quick Meeting 6) | 2015-03-02 | Begin work with Alex on audio handler | Calum | [15 empty] | Created | No
94 | 15 (Quick Meeting 6) | 2015-03-02 | Test Video Handler | Sam R. | [15 empty] | Created | In Progress
95 | 15 (Quick Meeting 6) | 2015-03-02 | Fill in category specific working hours online | Calum | [15 empty] | Created | Yes
96 | 16 (General Meeting 5) | 2015-03-04 | Draft spreadsheet to re-apply for loan | Emmanuel, Penny | [16 empty] | Created
97 | 16 (General Meeting 5) | 2015-03-04 | Track down Sam H. timesheet for financial report | Calum, Alex | [16 empty] | Created
98 | 16 (General Meeting 5) | 2015-03-04 | Alter user stories to better fit release specifications | Alex | [16 empty] | Created
99 | 16 (General Meeting 5) | 2015-03-04 | Translate release plan to KanBan tasks | Alex | [16 empty] | Created
100 | 16 (General Meeting 5) | 2015-03-04 | Look into .ogg and .m4a support without javaFX | Alex, Calum | [16 empty] | Created
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150