## Sheet1
Deliverable | Review Date | Deadline Date | Author | Reviewer 1 | Reviewer 2 | Pass/Fail | Comments
Functional Specification | 2015-01-29 | 2015-01-30 | Alex Cash | Sam | Ali | Pass | Good stuff, formatting could be better. Font? Looks good, all user stories relevent
QA Manual | 2015-02-01 | 2015-02-02 | Lewis Thresh + Others | Calum | Alex | Pass | QA Manual looks ok, some more in depth formatting might be nice, however content is all there. Worth to note that this document may need to change in the future
Financial Business Plan | 2015-02-06 | 2015-02-06 | Emmanuel Olutayo, Penny Nicole | Alex | Jake | Pass | Very quick review, completed on the day of the deadline. Good use of concise content, easy to read.
Project Wide Standards | 2015-02-12 | 2015-02-12 | Ali Jewers | Calum | Sam H | Pass | Fair and representitive of meeting agreeing these standards
Tender Presentation | 2015-02-15 | 2015-02-16 | ALL | Lewis | Sam H | Pass | All content is covered well. Unsure about level of finance.
Financial Report 1 | 2015-02-20 | 2015-02-20 | Emmanuel Olutayo, Penny Nicole | Sam R | Calum | Pass | Very quick review, completed on the day of the deadline. Assuming numbers are correct there should be no problem in submition
Contracts | 2015-02-23 | 2015-02-24 | Calum Armstrong | Alex | Lewis | Pass | Very thorough documents, well written. They should protect us should anything in the future go sour.
Financial Report 2 | 2015-03-05 | 2015-03-06 | Emmanuel Olutayo, Penny Nicole | Calum | Sam R | Pass | Report looks good, assuming all numbers are correct. Short but to the point.
Revised Financial Business Plan | 2015-03-06 | N/A | Emmanuel Olutayo, Penny Nicole | Alex | Sam R | Pass | Seems reasonable to me, I don't have the chance to run the numbers but everything makes sense to me and is clearly displayed. Assuming all numbers are correct I can see no issues.
Final Product Test Plan | 2015-03-12 | 2015-03-13 | Sam Raeburn | Ali | Alex | Pass | Might benefit from subheadings. Test methods seem solid; worth bearing in mind that it would be a good idea to re-run some earlier tests later on
Financial Report 3 | 2015-05-04 | 2015-05-01 | Emmanuel Olutayo, Penny Nicole | Jake | Sam R | Pass | Good work on picking up the discrepancies listed and how to rectify these.
Financial Summary Report | 2015-05-25 | 2015-05-22 | Emmanuel Olutayo, Penny Nicole | Sam H | Jake | Pass | Conclusion could be longer. Spreadsheet explanations look excellent. Nice and concise summary
Sales Presentation | 2015-06-01 | 2015-06-01 | ALL | Lewis | Sam H | Pass | All content seems relavent. Very close to the time limit.