## Sheet1
Task | Description | People Involved | Extra Work For
1. Pre-Iteration preparation
1.1 Assign team roles | Decide between the team who wants to take on which role | All
1.2 Initial product concept | Work together to produce ideas for a product to create | All
1.3 Organise infrastructure | Work to provide infrastructure to enable the team to complete their work (e.g. GitHub) | Alex Cash/All | Alex Cash
1.4 Create initial user stories | Capture what we require from the product and present the information in the form of user stories | All
1.5 Functional specification document | Produce a functional specification document to present to the client | Alex Cash | Alex Cash
1.6 QA Manual | Produce document outlining the company's methods and ethos regarding team work and producing deliverables | All
1.7 Financial plan | Create an initial financial plan to present to financial backer | Emmanuel and Penny | Emmanuel and Penny
2. Iteration 1
2.1 Iteration 1 planning | Decide which user stories to include in the first iteration and then plan how to go about implementing them | All
2.2 Iteration 1 Implementation and testing | Implement and continuously test the user stories previously decided on | All | Ali, Dan, Sam R
2.2.1 XML handling | Create an XML writer and parser | All
2.2.2 Page feature constructors | Create code structures enabling us to describle page elements that will feature in the lessons | All
2.2.3 Dummy GUI | Create a dummy GUI to test the XML handling
2.3 Iteration 1 verification | Ensure iteration 1 meets criteria and completes user stories | All | Sam R
3. Iteration 2
3.1 Iteration 2 planning | Decide which user stories to include in the second iteration and then plan how to go about implementing them | All
3.2 Iteration 2 implementation and testing | Implement and continuously test the user stories previously decided on | All | Ali, Dan, Sam R
3.3 Iteration 2 verification | Ensure iteration 2 meets criteria and completes user stories | All
4. Final product verification | Ensure that the final product meet sall requirements set by the client. Ensure that the product is stable. | All | Sam R
5. Project Wide Standards agreements | Agree on format of XML structure and media files with other companies involved | Calum Armstrong and Alex Cash | Calum Armstrong and Alex Cash
6. Group tender presentations | Initial presentation to showcase product concept and QA and design philosophy | All | Jake
7. Financial report 1 | Spreadsheet showing and justifying initial loan request | Emmanual and Penny | Emmanual and Penny
8. Software contracts agreed | Sales and purchasing of software agreed on | Callum Armstrong | Calum Armstrong
9. Financial report 2 | Spreadsheet showing current financial situation | Emmanuel and Penny | Emmanual and Penny
10. Submit implementation progress documents | Submit documentation showing progress made | All | Alex Cash
11. Submit final test and integration plan | Submit final plan outlining test and integration methods | Sam Raeburn and Alex Cash | Sam R
12. Financial report 3 | Spreadsheet showing current financial situation | Emmanual and Penny | Emmanual and Penny
13. Financial summary report | Report summarising finances from project | Emmanual and Penny | Emmanual and Penny
14. Demonstration and presentation | Demonstration of the created product and presentation to attempt to create sales | All | Jake, Alex
15. Submission of all deliverables | Submit all deliverables associated with the project | All | Alex Cash