## Sheet1
PREVIOUSLY: | week 3 | week 4 | week 5 | week 6
NO. OF HRS TOTAL - meetings: | 9.75 | 59.75 | 85 | 160.5 |  | < check that "Total hrs of week predicted" (column AH) compares to these
Spring Term
Deadlines | Week | Catagory | Penny Nicole |  |  | Alex Cash |  |  | Calum Armstrong |  |  | Alistair Jewers |  |  | Sam Raeburn |  |  | Sam Hall |  |  | Emmanuel Olutayo |  |  | Jake Ransom |  |  | Daniel Berhe |  |  | Lewis Thresh |  |  | Total hrs per Week Predicted | Total hrs per Week Actual | Total hrs per Week Varience
|  |  | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance | Predicted | Actual | Variance
| week 7 / 16th Feb | Marketing | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 | 1 | -1 | 0 |  | 0 | 0 |  | 0 | 3 | 1 | -2
|  | Presentations | 0.5 | 0.5 | 0 | 4 | 6 | 2 | 4 | 3.75 | -0.25 | 4 | 4 | 0 | 4 | 5 | 1 | 4 | 4 | 0 | 4 | 4 | 0 | 4 | 5 | 1 | 4 |  | -4 | 4 | 5 | 1 | 36.5 | 37.25 | 0.75
|  | Software Implementation | 0 |  | 0 | 10 | 11 | 1 | 2 |  | -2 | 10 | 14 | 4 | 2 |  | -2 | 3 |  | -3 | 0 |  | 0 | 6 | 4 | -2 | 5 | 9 | 4 | 2 |  | -2 | 40 | 38 | -2
|  | Testing | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 5 | 4 | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6 | 4 | -2
Finacial Report 1 |  | Finance | 10 | 7 | -3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 14 | 11 | -3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 24 | 18 | -6
|  | Administration | 0 |  | 0 | 0 |  | 0 | 6 | 12.25 | 6.25 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7 | 12.25 | 5.25
|  | Management | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3.5 | 0 | -3.5
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 12 | 2 | -10 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 | 2 | 0 | 15 | 4 | -11
|  | Total | 10.5 | 7.5 | -3 | 17 | 17 | 0 | 13 | 16 | 3 | 16 | 18 | 2 | 12 | 9 | -3 | 19.5 | 6 | -13.5 | 18 | 15 | -3 | 12 | 10 | -2 | 9 | 9 | 0 | 8 | 7 | -1 | 135 | 114.5 | -20.5
| Cumalative Total |  | 10.5 | 7.5 | -3 | 17 | 17 | 0 | 13 | 16 | 3 | 16 | 18 | 2 | 12 | 9 | -3 | 19.5 | 6 | -13.5 | 18 | 15 | -3 | 12 | 10 | -2 | 9 | 9 | 0 | 8 | 7 | -1 | 135 | 114.5 | -20.5
| week 8 / 23rd Feb | Marketing | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4 | 4 | 0 | 0 |  | 0 | 1 |  | -1 | 5 | 4 | -1
RIM draft report |  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 2 |  | -2 | 11 | 17 | 6 | 6 | 3 | -3 | 12 | 14 | 2 | 4 |  | -4 | 5 |  | -5 | 2 | 5 | 3 | 8 | 4 | -4 | 10 | 9.5 | -0.5 | 7 | 6.5 | -0.5 | 67 | 59 | -8
|  | Testing | 0 |  | 0 | 3 |  | -3 | 2 |  | -2 | 1 |  | -1 | 6 | 10 | 4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 12 | 10 | -2
Recalculate loan |  | Finance | 8 | 5 | -3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7 | 1 | -6 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 15 | 6 | -9
Contracts |  | Administration | 0 |  | 0 | 0 | 4 | 4 | 14 | 7.5 | -6.5 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5 |  | -5 | 20 | 11.5 | -8.5
|  | Management | 0 |  | 0 | 3 |  | -3 | 0 |  | 0 | 1 | 3 | 2 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 6 | 3 | -3
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 5 | 2 | -3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5 | 2 | -3 | 11 | 4 | -7
|  | Total | 10 | 5 | -5 | 17 | 21 | 4 | 22 | 10.5 | -11.5 | 15 | 17 | 2 | 12 | 10 | -2 | 10.5 | 2 | -8.5 | 9 | 6 | -3 | 12 | 8 | -4 | 10 | 9.5 | -0.5 | 18.5 | 8.5 | -10 | 136 | 97.5 | -38.5
| Cumalative Total |  | 20.5 | 12.5 | -8 | 34 | 38 | 4 | 35 | 26.5 | -8.5 | 31 | 35 | 4 | 24 | 19 | -5 | 30 | 8 | -22 | 27 | 21 | -6 | 24 | 18 | -6 | 19 | 18.5 | -0.5 | 26.5 | 15.5 | -11 | 271 | 212 | -59
| week 9 / 02nd Mar | Marketing | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 | 3 | 1 | 0 |  | 0 |  |  | 0 | 2 | 3 | 1
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 2 |  | -2 | 13 | 8 | -5 | 6 | 6 | 0 | 16 | 14 | -2 | 4 |  | -4 | 12 | 2 | -10 | 5 | 8.25 | 3.25 | 10 | 5.5 | -4.5 | 10 | 8.5 | -1.5 | 12 | 3 | -9 | 90 | 55.25 | -34.75
|  | Testing | 0 |  | 0 | 4 | 2 | -2 | 2 |  | -2 | 3 |  | -3 | 6 | 4 | -2 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 16 | 6 | -10
Financial Report 2 |  | Finance | 10 | 5 | -5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10 | 6 | -4 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 20 | 11 | -9
|  | Administration | 0 |  | 0 | 0 |  | 0 | 7 | 5 | -2 | 0 |  | 0 | 1 | 4 | 3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 8 | 9 | 1
|  | Management | 0 |  | 0 | 4 | 2 | -2 | 0 |  | 0 | 1 | 5 | 4 | 1 | 1 | 0 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 7 | 8 | 1
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 6 |  | -6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6 | 2 | -4 | 13 | 2 | -11
|  | Total | 12 | 5 | -7 | 21 | 12 | -9 | 15 | 11 | -4 | 21 | 19 | -2 | 12 | 9 | -3 | 19.5 | 2 | -17.5 | 15 | 14.25 | -0.75 | 12 | 8.5 | -3.5 | 10 | 8.5 | -1.5 | 18.5 | 5 | -13.5 | 156 | 94.25 | -61.75
| Cumalative Total |  | 32.5 | 17.5 | -15 | 55 | 50 | -5 | 50 | 37.5 | -12.5 | 52 | 54 | 2 | 36 | 28 | -8 | 49.5 | 10 | -39.5 | 42 | 35.25 | -6.75 | 36 | 26.5 | -9.5 | 29 | 27 | -2 | 45 | 20.5 | -24.5 | 427 | 306.25 | -120.75
RIM final report handin | week 10 / 09th Mar | Marketing | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 2 | 2.5 | 0.5 | 0 |  | 0 |  |  | 0 | 2 | 2.5 | 0.5
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Iteration 1' (Learn Easy) Complete |  | Software Implementation | 8 | 1 | -7 | 13 | 7.5 | -5.5 | 8 | 5 | -3 | 16 | 8 | -8 | 8 |  | -8 | 12 |  | -12 | 10 | 4 | -6 | 10 | 0.5 | -9.5 | 10 |  | -10 | 5 |  | -5 | 100 | 26 | -74
|  | Testing | 6 |  | -6 | 4 |  | -4 | 4 |  | -4 | 4 |  | -4 | 8 |  | -8 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 27 | 0 | -27
|  | Finance | 1 | 2.5 | 1.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 | 2 | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 3 | 4.5 | 1.5
|  | Administration | 0 | 0.25 | 0.25 | 0 |  | 0 | 6 | 2 | -4 | 0 | 8 | 8 | 1 | 7 | 6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 2.5 | 2.5 | 7 | 19.75 | 12.75
|  | Management | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 1 |  | -1 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 | 2 | 2 | 0.5 |  | -0.5 | 5 | 2 | -3
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 6 | 8 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 7 | 8 | 1
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Total | 15 | 3.75 | -11.25 | 19 | 7.5 | -11.5 | 18 | 7 | -11 | 22 | 16 | -6 | 18 | 7 | -11 | 19.5 | 8 | -11.5 | 12 | 6 | -6 | 12 | 3 | -9 | 10 | 2 | -8 | 5.5 | 2.5 | -3 | 151 | 62.75 | -88.25
|  | Cumalative Total | 47.5 | 21.25 | -26.25 | 74 | 57.5 | -16.5 | 68 | 44.5 | -23.5 | 74 | 70 | -4 | 54 | 35 | -19 | 69 | 18 | -51 | 54 | 41.25 | -12.75 | 48 | 29.5 | -18.5 | 39 | 29 | -10 | 50.5 | 23 | -27.5 | 578 | 369 | -209
| week 1 16th match | Marketing | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 7 | 5 | 0 | 0 | 0 |  |  | 0 | 2 | 7 | 5
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 10 |  | -10 | 10 |  | -10 | 6 |  | -6 | 12 |  | -12 | 8 |  | -8 | 6 |  | -6 | 7 |  | -7 | 12 |  | -12 | 10 |  | -10 | 8 |  | -8 | 89 | 0 | -89
|  | Testing | 6 |  | -6 | 2 |  | -2 | 3 |  | -3 | 2 |  | -2 | 10 |  | -10 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 25 | 0 | -25
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3 |  | -3 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 4 | 0 | -4
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 9 | 0 | -9
|  | Management | 0 |  | 0 | 3 | 1 | -2 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5 | 1 | -4
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12 | 20 | 8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10 | 11 | 1 | 22 | 31 | 9
|  | Total | 17 | 0 | -17 | 15 | 1 | -14 | 17 | 0 | -17 | 14 | 0 | -14 | 20 | 0 | -20 | 18.5 | 20 | 1.5 | 12 | 0 | -12 | 14 | 7 | -7 | 10 | 0 | -10 | 18.5 | 11 | -7.5 | 156 | 39 | -117
|  | Cumalative Total | 64.5 | 21.25 | -43.25 | 89 | 58.5 | -30.5 | 85 | 44.5 | -40.5 | 88 | 70 | -18 | 74 | 35 | -39 | 87.5 | 38 | -49.5 | 66 | 41.25 | -24.75 | 62 | 36.5 | -25.5 | 49 | 29 | -20 | 69 | 34 | -35 | 734 | 408 | -326
| week 2 23rd march | Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5.5 | 3.5 | 0 |  | 0 |  | 0 | 0 | 2 | 5.5 | 3.5
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 10 |  | -10 | 10 |  | -10 | 6 |  | -6 | 12 |  | -12 | 6 |  | -6 | 6 |  | -6 | 6 |  | -6 | 12 |  | -12 | 10 | 1 | -9 | 6 |  | -6 | 84 | 1 | -83
|  | Testing | 4 |  | -4 | 2 |  | -2 | 3 |  | -3 | 2 |  | -2 | 10 |  | -10 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 22 | 0 | -22
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 5 | 0 | -5
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 9 | 0 | -9
|  | Management | 0 |  | 0 | 3 |  | -3 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5 | 0 | -5
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12 |  | -12 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12 |  | -12 | 24 | 0 | -24
|  | Total | 15 | 0 | -15 | 15 | 0 | -15 | 17 | 0 | -17 | 14 | 0 | -14 | 18 | 0 | -18 | 18.5 | 0 | -18.5 | 11 | 0 | -11 | 14 | 5.5 | -8.5 | 10 | 1 | -9 | 18.5 | 0 | -18.5 | 151 | 6.5 | -144.5
|  | Cumalative Total | 79.5 | 21.25 | -58.25 | 104 | 58.5 | -45.5 | 102 | 44.5 | -57.5 | 102 | 70 | -32 | 92 | 35 | -57 | 106 | 38 | -68 | 77 | 41.25 | -35.75 | 76 | 42 | -34 | 59 | 30 | -29 | 87.5 | 34 | -53.5 | 885 | 414.5 | -470.5
| week 3 30th march | Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 0 | -2 | 0 | 0 | 0 |  | 0 | 0 | 2 | 0 | -2
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 10 |  | -10 | 10 |  | -10 | 6 |  | -6 | 12 |  | -12 | 8 |  | -8 | 6 |  | -6 | 6 |  | -6 | 12 |  | -12 | 10 |  | -10 | 6 |  | -6 | 86 | 0 | -86
|  | Testing | 6 |  | -6 | 2 |  | -2 | 3 |  | -3 | 2 |  | -2 | 8 |  | -8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 21 | 0 | -21
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 3 | 0 | -3
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 9 | 0 | -9
|  | Management | 0 |  | 0 | 3 |  | -3 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5 | 0 | -5
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12 | 20 | 8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10 |  | -10 | 22 | 20 | -2
|  | Total | 17 | 0 | -17 | 15 | 0 | -15 | 17 | 0 | -17 | 14 | 0 | -14 | 18 | 0 | -18 | 18.5 | 20 | 1.5 | 8 | 0 | -8 | 14 | 0 | -14 | 10 | 0 | -10 | 16.5 | 0 | -16.5 | 148 | 20 | -128
|  | Cumalative Total | 96.5 | 21.25 | -75.25 | 119 | 58.5 | -60.5 | 119 | 44.5 | -74.5 | 116 | 70 | -46 | 110 | 35 | -75 | 124.5 | 58 | -66.5 | 85 | 41.25 | -43.75 | 90 | 42 | -48 | 69 | 30 | -39 | 104 | 34 | -70 | 1033 | 434.5 | -598.5
| week 4 6th april | Marketing | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 1 | -1 | 0 | 0 | 0 |  | 0 | 0 | 2 | 1 | -1
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 10 |  | -10 | 10 | 9 | -1 | 6 |  | -6 | 12 | 12 | 0 | 8 |  | -8 | 6 |  | -6 | 6 |  | -6 | 12 |  | -12 | 10 |  | -10 | 6 |  | -6 | 86 | 21 | -65
|  | Testing | 6 |  | -6 | 2 |  | -2 | 3 |  | -3 | 2 |  | -2 | 10 |  | -10 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 24 | 0 | -24
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 3 |  | -3 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 6 | 0 | -6
|  | Administration | 0 |  | 0 | 0 |  | 0 | 6 |  | -6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 6 | 0 | -6
|  | Management | 0 |  | 0 | 3 | 1 | -2 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5 | 1 | -4
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12 | 20 | 8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10 |  | -10 | 22 | 20 | -2
|  | Total | 17 | 0 | -17 | 15 | 10 | -5 | 15 | 0 | -15 | 17 | 12 | -5 | 19 | 0 | -19 | 18.5 | 20 | 1.5 | 9 | 0 | -9 | 14 | 1 | -13 | 10 | 0 | -10 | 16.5 | 0 | -16.5 | 151 | 43 | -108
|  | Cumalative Total | 113.5 | 21.25 | -92.25 | 134 | 68.5 | -65.5 | 134 | 44.5 | -89.5 | 133 | 82 | -51 | 129 | 35 | -94 | 143 | 78 | -65 | 94 | 41.25 | -52.75 | 104 | 43 | -61 | 79 | 30 | -49 | 120.5 | 34 | -86.5 | 1184 | 477.5 | -706.5
PhysMod report handin | week 1 13th april | Marketing | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 0 | -2 | 10 | 0 | -10 |  |  | 0 | 12 | 0 | -12
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5 |  | -5 | 5 | 0 | -5
|  | Software Implementation | 8 |  | -8 | 12 |  | -12 | 2 |  | -2 | 14 |  | -14 | 4 |  | -4 | 8 |  | -8 | 8 |  | -8 | 12 |  | -12 | 0 |  | 0 |  |  | 0 | 68 | 0 | -68
|  | Testing | 4 |  | -4 | 3 |  | -3 | 1 |  | -1 | 2 |  | -2 | 11 |  | -11 | 1 |  | -1 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 23 | 0 | -23
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 3 | 0 | -3
|  | Administration | 0 |  | 0 | 0 |  | 0 | 4 | 1 | -3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 4 | 1 | -3
|  | Management | 0 |  | 0 | 3 | 2 | -1 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5 | 2 | -3
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 6 | 8 | 2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 11.75 | 11.75 | 8 | 19.75 | 11.75
|  | Total | 13 | 0 | -13 | 18 | 2 | -16 | 7 | 1 | -6 | 18 | 0 | -18 | 16 | 0 | -16 | 15.5 | 8 | -7.5 | 11 | 0 | -11 | 14 | 0 | -14 | 10 | 0 | -10 | 5.5 | 11.75 | 6.25 | 128 | 22.75 | -105.25
|  | Cumalative Total | 126.5 | 21.25 | -105.25 | 152 | 70.5 | -81.5 | 141 | 45.5 | -95.5 | 151 | 82 | -69 | 145 | 35 | -110 | 158.5 | 86 | -72.5 | 105 | 41.25 | -63.75 | 118 | 43 | -75 | 89 | 30 | -59 | 126 | 45.75 | -80.25 | 1312 | 500.25 | -811.75
DesCon demonstration | week 2 20th april | Marketing | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 1 | -1 | 0 | 0 | 0 |  | 0 | 0 | 2 | 1 | -1
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 8 |  | -8 | 12 |  | -12 | 6 |  | -6 | 12 | 20 | 8 | 4 |  | -4 | 8 |  | -8 | 2 |  | -2 | 12 |  | -12 | 10 |  | -10 | 8 |  | -8 | 82 | 20 | -62
|  | Testing | 2 |  | -2 | 3 |  | -3 | 3 |  | -3 | 1 |  | -1 | 8 | 2 | -6 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 18 | 2 | -16
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 3 | 0 | -3
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 8 | 0 | -8
|  | Management | 0 |  | 0 | 3 | 1 | -2 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5 | 1 | -4
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6 | 8 | 2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6 |  | -6 | 12 | 8 | -4
|  | Total | 11 | 0 | -11 | 18 | 1 | -17 | 17 | 0 | -17 | 13 | 20 | 7 | 13 | 2 | -11 | 15.5 | 8 | -7.5 | 4 | 0 | -4 | 14 | 1 | -13 | 10 | 0 | -10 | 14.5 | 0 | -14.5 | 130 | 32 | -98
|  | Cumalative Total | 137.5 | 21.25 | -116.25 | 170 | 71.5 | -98.5 | 158 | 45.5 | -112.5 | 164 | 102 | -62 | 158 | 37 | -121 | 174 | 94 | -80 | 109 | 41.25 | -67.75 | 132 | 44 | -88 | 99 | 30 | -69 | 140.5 | 45.75 | -94.75 | 1442 | 532.25 | -909.75
DesCon Report | week 3 27th Apr | Marketing | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | 1.5 | -0.5 | 0 |  | 0 |  |  | 0 | 2 | 1.5 | -0.5
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 2 | 1.75 | -0.25 | 10 | 4 | -6 | 6 | 1.75 | -4.25 | 12 | 4 | -8 | 4 | 6.5 | 2.5 | 4 |  | -4 | 2 | 3 | 1 | 12 | 1.5 | -10.5 | 10 | 3 | -7 | 4 | 5.5 | 1.5 | 66 | 31 | -35
|  | Testing | 1 |  | -1 | 3 |  | -3 | 3 |  | -3 | 2 |  | -2 | 8 |  | -8 | 1 |  | -1 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 19 | 0 | -19
Financial Report 3 |  | Finance | 10 | 4 | -6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 18 | 4 | -14 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 28 | 8 | -20
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 | 8 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 8 | 8 | 0
|  | Management | 0 |  | 0 | 5 | 0.5 | -4.5 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 7 | 0.5 | -6.5
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 3 |  | -3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3 |  | -3 | 7 | 0 | -7
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Total | 13 | 5.75 | -7.25 | 18 | 4.5 | -13.5 | 17 | 9.75 | -7.25 | 15 | 4 | -11 | 13 | 6.5 | -6.5 | 8.5 | 0 | -8.5 | 21 | 7 | -14 | 14 | 3 | -11 | 10 | 3 | -7 | 7.5 | 5.5 | -2 | 137 | 49 | -88
|  | Cumalative Total | 150.5 | 27 | -123.5 | 188 | 76 | -112 | 175 | 55.25 | -119.75 | 179 | 106 | -73 | 171 | 43.5 | -127.5 | 182.5 | 94 | -88.5 | 130 | 48.25 | -81.75 | 146 | 47 | -99 | 109 | 33 | -76 | 148 | 51.25 | -96.75 | 1579 | 581.25 | -997.75
| week 4 4th May | Marketing | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -2 | 0 | 0 | 0 |  | 0 | 0 | 2 | 0 | -2
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Software Implementation | 8 |  | -8 | 12 |  | -12 | 6 | 6 | 0 | 12 |  | -12 | 4 |  | -4 | 8 |  | -8 | 6 |  | -6 | 12 |  | -12 | 10 |  | -10 | 4 |  | -4 | 82 | 6 | -76
|  | Testing | 4 |  | -4 | 2 |  | -2 | 3 |  | -3 | 2 |  | -2 | 8 |  | -8 | 1 |  | -1 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 21 | 0 | -21
|  | Finance | 1 | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 5 | 1 | -4
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 8 | 0 | -8
|  | Management | 0 |  | 0 | 3 | 0.5 | -2.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 4 | 0.5 | -3.5
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 6 |  | -6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3 |  | -3 | 10 | 0 | -10
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Total | 13 | 1 | -12 | 17 | 0.5 | -16.5 | 17 | 6 | -11 | 15 | 0 | -15 | 12 | 0 | -12 | 15.5 | 0 | -15.5 | 11 | 0 | -11 | 14 | 0 | -14 | 10 | 0 | -10 | 7.5 | 0 | -7.5 | 132 | 7.5 | -124.5
|  | Cumalative Total | 163.5 | 28 | -135.5 | 205 | 76.5 | -128.5 | 192 | 61.25 | -130.75 | 194 | 106 | -88 | 183 | 43.5 | -139.5 | 198 | 94 | -104 | 141 | 48.25 | -92.75 | 160 | 47 | -113 | 119 | 33 | -86 | 155.5 | 51.25 | -104.25 | 1711 | 588.75 | -1122.25
Neural Networks Exam | week 5 11th May | Marketing | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 |  | 2 | 2 | 2 | 4 | 2
|  | Presentations | 0 |  | 0 | 0 |  | 0 | 0 | 3 | 3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 2 | 2 | 0 | 5 | 5
Filters Exam |  | Software Implementation | 6 |  | -6 | 10 |  | -10 | 6 |  | -6 | 12 | 3 | -9 | 4 |  | -4 | 8 |  | -8 | 0 |  | 0 | 12 |  | -12 | 10 |  | -10 | 10 | 5 | -5 | 78 | 8 | -70
|  | Testing | 4 |  | -4 | 3 |  | -3 | 3 |  | -3 | 2 |  | -2 | 8 |  | -8 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 21 | 0 | -21
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 1 | 0 | -1
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 | 6 | -2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 8 | 6 | -2
|  | Management | 0 |  | 0 | 3 | 1 | -2 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0.5 |  | -0.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5 | 1 | -4
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 6 | 2 | -4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6 |  | -6 | 13 | 2 | -11
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Total | 11 | 0 | -11 | 16 | 1 | -15 | 17 | 9 | -8 | 15 | 3 | -12 | 13 | 0 | -13 | 15.5 | 2 | -13.5 | 0 | 0 | 0 | 14 | 2 | -12 | 10 | 0 | -10 | 16.5 | 9 | -7.5 | 128 | 26 | -102
|  | Cumalative Total | 174.5 | 28 | -146.5 | 221 | 77.5 | -143.5 | 209 | 70.25 | -138.75 | 209 | 109 | -100 | 196 | 43.5 | -152.5 | 213.5 | 96 | -117.5 | 141 | 48.25 | -92.75 | 174 | 49 | -125 | 129 | 33 | -96 | 172 | 60.25 | -111.75 | 1839 | 614.75 | -1224.25
Distributed Computer Systems Report Due | week 6 18th May | Marketing | 0 |  | 0 | 0 |  | 0 | 0 | 11 | 11 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 11.5 | 7.5 | 0 |  | 0 |  | 26.5 | 26.5 | 4 | 49 | 45
|  | Presentations | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 4 | 0 | -4
|  | Software Implementation | 2 | 18 | 16 | 12 | 3 | -9 | 6 |  | -6 | 14 | 22 | 8 | 4 | 1 | -3 | 10 |  | -10 | 2 |  | -2 | 12 |  | -12 | 10 | 40 | 30 | 12 | 20.5 | 8.5 | 84 | 104.5 | 20.5
|  | Testing | 1 |  | -1 | 3 |  | -3 | 3 |  | -3 | 4 |  | -4 | 8 | 12 | 4 | 2 |  | -2 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 22 | 12 | -10
Finance Summary Report |  | Finance | 15 |  | -15 | 0 |  | 0 | 0 | 9 | 9 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12 | 14 | 2 | 0 | 5.75 | 5.75 | 0 |  | 0 |  | 4.5 | 4.5 | 27 | 33.25 | 6.25
|  | Administration | 0 |  | 0 | 0 |  | 0 | 8 | 29 | 21 | 0 |  | 0 | 0 | 4 | 4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 8 | 33 | 25
|  | Management | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5.5 | 0 | -5.5
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 11 | 0 | -11
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Total | 18 | 18 | 0 | 23 | 3 | -20 | 17 | 49 | 32 | 20 | 22 | 2 | 13 | 17 | 4 | 20 | 0 | -20 | 15 | 14 | -1 | 16 | 17.25 | 1.25 | 10 | 40 | 30 | 13.5 | 51.5 | 38 | 165.5 | 231.75 | 66.25
|  | Cumalative Total | 192.5 | 46 | -146.5 | 244 | 80.5 | -163.5 | 226 | 119.25 | -106.75 | 229 | 131 | -98 | 209 | 60.5 | -148.5 | 233.5 | 96 | -137.5 | 156 | 62.25 | -93.75 | 190 | 66.25 | -123.75 | 139 | 73 | -66 | 185.5 | 111.75 | -73.75 | 2004.5 | 846.5 | -1158
| week 7 | Marketing | 2 |  | -2 | 2 |  | -2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10 |  | -10 | 2 |  | -2 | 0 |  | 0 |  |  | 0 | 16 | 0 | -16
|  | Presentations | 5 | 10.5 | 5.5 | 8 | 27 | 19 | 14 | 46 | 32 | 0 | 41 | 41 | 0 | 68 | 68 | 0 | 29 | 29 | 0 | 15 | 15 | 0 | 45 | 45 | 0 | 49 | 49 | 20 | 33.5 | 13.5 | 47 | 364 | 317
|  | Software Implementation | 4 | 3 | -1 | 11 | 22 | 11 | 6 |  | -6 | 20 | 39 | 19 | 4 | 4 | 0 | 10 |  | -10 | 3 |  | -3 | 12 |  | -12 | 10 |  | -10 | 12 | 2 | -10 | 92 | 70 | -22
|  | Testing | 2 |  | -2 | 4 |  | -4 | 3 |  | -3 | 4 |  | -4 | 8 | 6 | -2 | 2 |  | -2 | 2 |  | -2 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 25 | 6 | -19
|  | Finance | 4 | 4.5 | 0.5 | 0 |  | 0 | 0 | 13 | 13 | 0 |  | 0 | 0 |  | 0 | 0 | 24 | 24 | 6 | 4 | -2 | 0 | 5.5 | 5.5 | 0 |  | 0 |  | 2 | 2 | 10 | 53 | 43
|  | Administration | 0 |  | 0 | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 4 | 0 | -4
|  | Management | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.5 |  | -0.5 | 5.5 | 0 | -5.5
|  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 19 | 18 | 11 | 19 | 8
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Total | 17 | 18 | 1 | 29 | 49 | 20 | 27 | 59 | 32 | 26 | 80 | 54 | 13 | 78 | 65 | 20 | 53 | 33 | 21 | 19 | -2 | 14 | 50.5 | 36.5 | 10 | 49 | 39 | 33.5 | 56.5 | 23 | 210.5 | 512 | 301.5
|  | Cumalative Total | 209.5 | 64 | -145.5 | 273 | 129.5 | -143.5 | 253 | 178.25 | -74.75 | 255 | 211 | -44 | 222 | 138.5 | -83.5 | 253.5 | 149 | -104.5 | 177 | 81.25 | -95.75 | 204 | 116.75 | -87.25 | 149 | 122 | -27 | 219 | 168.25 | -50.75 | 2215 | 1358.5 | -856.5
Should be done by now really | week 8 | Marketing | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 |  |  | 0 | 2 | 0 | -2
|  | Presentations | 0.5 |  | -0.5 | 0 |  | 0 | 10 |  | -10 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 |  |  | 0 | 14.5 | 0 | -14.5
Demonstration and Sales Presentation |  | Software Implementation | 4 |  | -4 | 2 |  | -2 | 6 |  | -6 | 24 |  | -24 | 0 |  | 0 | 16 |  | -16 | 17 |  | -17 | 12 |  | -12 | 10 |  | -10 | 12 |  | -12 | 103 | 0 | -103
|  | Testing | 4 |  | -4 | 6 |  | -6 | 3 |  | -3 | 6 |  | -6 | 20 |  | -20 | 6 |  | -6 | 3 |  | -3 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 48 | 0 | -48
|  | Finance | 1 |  | -1 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5 |  | -5 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 6 | 0 | -6
^ DaSP due on mon, so put |  | Administration | 0 |  | 0 | 0 |  | 0 | 4 |  | -4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 4 | 0 | -4
|  | Management | 0 |  | 0 | 6 |  | -6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 6 | 0 | -6
working hours in week 7? |  | User experience | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2 |  | -2 | 0 |  | 0 | 8 |  | -8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 |  | -1 | 11 | 0 | -11
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Total | 9.5 | 0 | -9.5 | 14 | 0 | -14 | 23 | 0 | -23 | 32 | 0 | -32 | 20 | 0 | -20 | 30 | 0 | -30 | 25 | 0 | -25 | 18 | 0 | -18 | 10 | 0 | -10 | 13 | 0 | -13 | 194.5 | 0 | -194.5
|  | Cumalative Total | 219 | 64 | -155 | 287 | 129.5 | -157.5 | 276 | 178.25 | -97.75 | 287 | 211 | -76 | 242 | 138.5 | -103.5 | 283.5 | 149 | -134.5 | 202 | 81.25 | -120.75 | 222 | 116.75 | -105.25 | 159 | 122 | -37 | 232 | 168.25 | -63.75 | 2409.5 | 1358.5 | -1051
| Grand Total |  | 219 | 64 | -155 | 287 | 129.5 | -157.5 | 276 | 178.25 | -97.75 | 287 | 211 | -76 | 242 | 138.5 | -103.5 | 283.5 | 149 | -134.5 | 202 | 81.25 | -120.75 | 222 | 116.75 | -105.25 | 159 | 122 | -37 | 232 | 168.25 | -63.75 | 2409.5
[29 empty] | Total Company Hours |  | Predicted | 2409.5
[31 empty] | Actual | 1358.5
[31 empty] | Variance | 1051